## Roadmap
INTERNAL ROADMAP
Hypothesis-driven · Every initiative traces back to a validated job | [5 empty] | Version 1.0
HORIZON | INITIATIVE | LINKED JTBD | HYPOTHESIS "We believe..." | SIGNAL / EVIDENCE What validated this | SUCCESS METRIC "We'll know it worked when..." | STATUS | CONFIDENCE | OWNER
NOW | Request ride flow | When I need to get somewhere, I want to request a ride instantly so I can plan my time | We believe showing upfront fare + ETA before confirmation reduces booking anxiety and increases conversion | Discovery interviews: 8/10 riders said price uncertainty was #1 friction | Booking completion rate ≥ 70% in prototype usability test | Testing | High | Founder
NOW | Driver matching screen | When I need to get somewhere, I want to see my driver details so I can feel confident the ride is real | We believe showing driver name, photo, and car details immediately after match reduces cancellations | Validated: riders cancelled 3x more when driver info was delayed | Cancel rate < 10% post-match in first 50 rides | Validated | High | Founder
NOW | Live driver location map | When I need to get somewhere, I want to track my driver so I can know exactly when to leave | We believe real-time map tracking reduces "where is my driver?" support contacts by 60%+ | Hypothesis — not yet tested | Support contacts re: driver location < 5% of rides | Untested | Medium | Founder
NEXT | Fare split feature | When I share a ride with others, I want to split the fare automatically so I can avoid awkward payment moments | We believe in-app fare split increases group ride frequency by removing post-ride friction | Partial signal: 40% of riders surveyed mentioned splitting payment as a pain point | Group ride bookings increase 25% MoM after launch | Untested | Medium | TBD
NEXT | Scheduled rides | When I have a fixed appointment, I want to book a ride in advance so I can eliminate last-minute stress | We believe advance booking unlocks airport and commute use cases that add a 2nd daily ride occasion | Market analogy: Lyft scheduled rides drove 18% incremental bookings | Scheduled rides = 20%+ of total bookings within 60 days | Untested | Low | TBD
LATER | Driver ratings & reviews | When I complete a ride, I want to rate my driver so I can help others make informed choices | We believe a 2-way rating system improves driver quality and rider trust over time | Standard in category — directional only | Average driver rating ≥ 4.6 after 90 days of ratings | Untested | Low | TBD
LATER | Subscription / membership tier | When I ride frequently, I want a membership plan so I can reduce per-ride cost and feel like a priority customer | We believe a monthly pass increases ride frequency 2x and reduces churn for power users | No current signal — needs discovery before committing | Subscriber LTV > 3x non-subscriber within 6 months | Untested | Low | TBD

## How to Use
HOW TO USE THIS ROADMAP
A hypothesis-driven internal roadmap for early-stage founders
THE PHILOSOPHY
This is not a feature list. | Every row is a bet — a hypothesis about what will move an outcome for a specific user job.
Traceability is the discipline. | If an initiative cannot be linked to a validated JTBD, it should not be on the roadmap.
Status is honest. | Untested is fine. Most of your roadmap should be Untested in early stages. That's the point.
Invalidated is data, not failure. | When a hypothesis fails, mark it Invalidated and learn from it before moving to the next bet.
COLUMN GUIDE
Horizon | NOW = active this cycle (3–5 items max). NEXT = conditional on NOW results. LATER = directional, low commitment.
Initiative | The thing you're building. Name it clearly — avoid vague labels like "improve onboarding."
Linked JTBD | Paste the exact JTBD statement this initiative serves. One job per row. If you can't fill this, the initiative may not belong here.
Hypothesis | Start with "We believe..." — what outcome do you expect this initiative to create, and why? Be falsifiable.
Signal / Evidence | What customer evidence, interview data, or market signal supports this hypothesis? Be honest about strength of signal.
Success Metric | Start with "We'll know it worked when..." — one measurable outcome. Not a vanity metric.
Status | Untested → Testing → Validated or Invalidated. Move rows honestly as you learn.
Confidence | How strong is your evidence? High = multiple validated signals. Medium = partial signal. Low = directional only.
Owner | Who is responsible for moving this forward? For solo founders: still useful to name it.
STATUS LEGEND
Untested | Hypothesis formed but no discovery or experiment run yet. Default state.
Testing | Actively running interviews, experiments, or a prototype with users.
Validated | Evidence supports the hypothesis. Confident enough to build.
Invalidated | Evidence contradicts the hypothesis. Do not proceed — learn and reframe.